## PBI
Product Backlog Items
Story # | Product Backlog Items | User Story | Requirements | Acceptance criteria | Estimation points | Justification for the duration | Definition of done | Priority (based on Business Value)
2 | Home page | As a user, I want to view the links of other webpages and websites for further detailed information. | The home page must allow the user to select the language preference. | The drop-down bar contains all the languages depending on the region of the user by requesting permission to access the user's location. | 3 | Integration with geo-location API is complicated and not compatible by some browsers. Development of feature detection would take longer. | The user must find all the functional features within this page. | 1
|  |  | The homepage must contain a search bar at the top right corner to navigate for filtered information. | The search bar must be fixed so that it is visible at any part of the page . | 2 | Minor changes to a couple lines of code and testing these code.
|  |  | The homepage consists of an index of different sections with appropriate hyperlinks. | A click on the section should take the user to the desired page in a new tab. | 5 | Creating hyperlinks and connecting them with the appropriate file is a lengthy process and testing each link too. Therefore, 3 points and 2 points is allocated for the former and latter respectively.
1 | Image | As a user, I want to view the image of Cheetah as soon as I open the website | The image has a high resolution with aspect ratio of 16:9. | The image would be clear even if the image is zoomed 10X. | 1 | A high quality image can be easily uploaded and tested using the Paint application. | The Cheetah's image on the website can be downloaded by the user multiple times in any format | 2
|  |  | The image is alligned at the centre of the page | The image will remain at the centre of the page even if the user opens it another browser or scrolls down the page. | 2 | Allignment test would require publishing the page offline and then alter in case of shifts.
|  |  | The text does not overlap with the image | The padding between the image and text is atleast 170 px | 1 | By setting the distance on the word file itself, this problem can be eliminated and tested within a short time
3 | Diet information | As a user, I want to learn about the diet information of the Cheetah | The text of this web page have the detailed information about what the Cheetah eats, how often and what amount. | A cheetah expert must validate the information | 3 | The Cheetah expert would take time to read and make changes to the content | The user obtains all the possible information on Cheetah's diet accurately | 3
|  |  | This page have at least three image of the main food items of the Cheetah | The cheetah is eating the food item in each of the images | 2 | The images are found easily on different books, websites
|  |  | This page contains at least five links to external resources with more details on individual food items. | The user must gain additional, true information about the Cheetah'diet. Wikipedia must not be part of these resources. Each resource must be verifiable by the American Humane organization | 5 | External resources must be shortlisted to obtain the most concise and accurate representation of Cheetah's diet. These resources would have to be verified for its content through the organization. It may take consume 5 points
| Mating & Reproduction | As a user, I want to learn about the mating and reproduction information of the Cheetah. | The web page should have the information about the gestational period of the animal. | Given I’m in a role of logged-in or guest user, When I open the "Mating&reproduction" page, the webpage containing the hyperlink to describe Cheetahs' gestional period must be displayed. | 5 | The process of the collection and the compilation of the valid and correct information about the gestion of Cheetah, and the process of verifying the validity of the information cosnsumes 5 points. | The user can find all the relevant information within this page. | 4
|  |  | The webpage should have the information about the numbers of the cheetah’s offspring at a time, | Given I’m in a role of logged-in or guest user, When I open the "Mating&reproduction" page, after the text of gestional period of the Cheetah, then the webpage show me the texts and pictures that descripe the numbers of the cheetah’s offspring at a time. | 5 | These collected external resources would have to be compiled for its layout on the web page by the develop team and verified for its content through the organization. It may take upto 5 days in total.
|  |  | The text of this web page should have the information about how long do the offspring live with the parent. | Given I’m in a role of logged-in or guest user, When I open the "Mating&reproduction" page, in the last part, the webpage shows me the texts and that descripe how long do the offspring live with the parent. | 5 | The develop team would need up to five day to collect the information about the Cheetah's offspring and gain the right to cite and use these information from the external organization for building this web page.
| Habitat | As a user, I want to learn about the habitat information of the Cheetah. | This page should contain the text and a map about the location and distribution of the Cheetah’s habitat. | Given I’m in a role of logged-in or guest user, When I open the "Habitat" page, then the webpage firstly show me the text that descripe where do the Cheetah mainly live and a distribuation map that visalluy show the location of the Cheetah's habitat. | 5 | External resources must be rearrangedand re-organized to obtain the most concise and accurate representation of Cheetah's location and distribuation. These resources would have to be verified for its content through the American Humane Organization. It will take long. | All the information/links are approved by product owner before it being published. | 5
|  |  | This page should contain the text and at least 1 picture about the necessary and required natural surrounding for the Cheetah to thrive | Given I’m in a role of logged-in or guest user, When I open the "Habitat" page, after the text and picture of the location and distribution of Cheetah,then the webpage show me a picture that vividly show the natural surrounding og the Cheetah's life. | 5 | The develop team need to select the image that can completely show the natural surrounding of the Cheetah's life with high resolution, which means the image is clear even if it is zoomed 10X by the users and they can clearly see the detial of the image.
|  |  | This page should contain the text and at least 1 picture about construction of Cheetah's home. | Given I’m in a role of logged-in or guest user, When I open the "Habitat" page, in the last part of this page,it show me the texts that describe where and how the Cheetah make their home and a picture that show the example of the Cheetah's home made by themselves. | 5 | The develop team should make sure the text show the correct description of where and how the Cheetah make their home , and the picture show the real and realistic Cheetah's home. These works would take 5 points.
| Scientific name and classification | As a user, I want to know the scientific name and classification of the cheetah, their primary species and subspecies | There will be images of species of Cheetah. | Images of the specie are shown with one click on the species text. | 2 | The images are taken from popular and verified books based on Cheetah and research | The user can find all the information regarding classification on this page. | 6
|  |  | There will be information on the species and subspecies of Cheetah | Data would be collected from reputed publications with verification | 3 | The data collection would take 2 pointsand 1 point would be consumed for verifying the collected data
|  |  | There will be scientific name and characteristics of cheetah on the page in table format | Data would be collected from reputed publications with verification | 3 | The data collection would take 2 days and 1 day would be consumed for verifying the collected data
| Anatomy and Biology | As a user, I want to know about the height, weight or general size information of the cheetah, and its lifespan | There will be general size information below the image of cheetah | Verified by zookeepers and Cheetah experts. | 2 | The data collection and verification shall take 1 day each | The user can find information regarding cheetah's life with all the images of general size information | 7
|  |  | There will be unique physical characteristics of cheetah on the webpage | Verified by zookeepers and Cheetah experts | 2 | The data collection and verification shall take
|  |  | Lifespan and heart rate of the cheetah is mentioned in health part | Verified by zookeepers and Cheetah experts. | 2 | The data collection and verification
| Behavior | As a user, I want to know about the shelter,hunting methods cheetah uses to get food and protect themselves from other animals and their sleeping habits. | Hunting techniques of the cheetah is picturized | The different hunting techniques and their images are provided by zookeepers. | 1 | The images would have to be requested from the zookeepers and permission | The user can find information and images of the food and diet plan of cheetah and the images of their place for shelter. | 8
|  |  | Blog for cheetah's self protection is written with 3 pictures | Cheetah enthusiast start writing blogs under the supervision of a Cheetah guide | 3 | The blog must contain information with evidence. Evidence collection may take 2 points while writing and editing the blog consumes one point
|  |  | Sleeping habits are shown in the form of text and images | The Veterinary expert must confirm the information | 2 | The expert must read the content before verification
4 | Interface | As a user, I want to get access to a high quality, well-researched information without any difficulty. | Each webpage must be tested to verify the data present. | Texts and images must be referenced from authorized and trusted sources | 5 | Finding interesting, useful, authorized texts and images about the Cheetahs and testing each webpage demands a lot of attention and time. | No error shall occur if the user clicks on any section of the website | 9
|  |  | Each link must contain an existing domain name. | Each link must be accessed by one click. | 2 | The number of links demands at least 2 points for doing this work successfully.
|  |  | Each line of the code must be tested to ensure accuracy. | Each code must be more than 8 symbols. Each code must include capital letter(s), lower case letters, symbols. | 2 | Each code must be unique and each code has some requirements must be met. Each line of the code must be tested.
6 | New content | As a user I want to see updated news and pictures about the cheetahs on a home page every day | The news in the home page must be updated every day. | User must be able to get notification about updated news. | 5 | Creating a link for the sharing news, sending notification to users are long processes. So, it will take at least 5 days. | The user must be able to obtain notifications on new pictures and news. | 10
|  |  | The pictures in the home page must be updated every alternate day. | User must be able to get notification about updated images. | 3 | Creating a link for the sharing pictures, sending notification to users are long processes. So, it will be moderate units.
|  |  | The users must be notified of the updates on the email address and social media accounts. | The users must be given choices about being notified of the updates via: 1) mobile number 2) e-mail 3) social media accounts. | 3 | Five hyperlinks must be created for this function. Plus, each link must be tested. So, this process will take 3 points.
5 | User-feedback capability | As a user, I want to actively participate on the website | The user must be able to comment, like or dislike any information on the page. | A user must be able to like/dislike by one click. A user will type his/her comment and press "enter" for commenting. | 1 | Like/Dislike/ and comment functions is easy. So, a day will be enough for creating these functions. | The user has all the resources to share his/her views | 11
|  |  | The user must be able to share the links on other websites and social media accounts | A user must be able to share links only about cheetahs. A user will click on "share" button and will choose any social media account where wants to share links about cheetahs. | 1 | Share function can be executed in a simple manner.
|  |  | A user must be able to register themselves through their social network accounts and connect with other users. | A user must be given choices: 1) Register via social media 2) Register via email | 3 | Two hyperlinks must be created for register choices and they must be connected with the appropriate links. So this process will consume moderate units
6 | Live streaming capability | As a user, I want to watch the Cheetah live | A user must be able to track the movements of Cheetah. A registered user must be able to record and download short clips while streaming | The user must be able to switch between the monitor screens to view the Cheetah. An extension on the browser must be created that would record the video in a mp4 format with high resolution | 4 | Integration with the camera and satellites would take time. Creating web extension and capability for the download feature will consume time. | The user can watch the Cheetah at any time from different angles | 12
|  |  | A guest user should be able to view the footage for only 2 hours. A registered user must gain unlimited access to the live stream. | A timer shall run that would prevent guest users access into the streaming feature by turning the link obsolete | 2 | A simple timing application locked on to the user's webpage would suffice, consuming 1 point
|  |  | A registered user must be able to engage in live chats with Cheetah experts and other users | A click option must be available to initiate chats with others | 1 | A link to the chatbox is easy to create and the team is highly equipped to achieve this

## Sprint
The sprint backlog has been decided based on the business value- feature specific(not exceeding 16 points/sprint)
| Sprints | Feature | User stories | Points
| Sprint 1 | Language | The home page must allow the user to select the language preference | 3
|  | Navigation bar | The homepage must contain a search bar at the top right corner to navigate for filtered information | 2
|  | Index | The homepage consists of an index of different sections with appropriate hyperlinks | 5
|  | Cheetah's image resolution | The image has a high resolution with aspect ratio of 16:9 | 1
|  | Cheetah's image alignment | The image is alligned at the centre of the page | 2
|  | Cheetah's image-information spacing | The text does not overlap with the image | 1
| Sprint 2 | Cheetah eating habits | The text of this web page have the detailed information about what the Cheetah eats, how often and what amount. | 3
|  | Images of Cheetah's food | This page have at least three image of the main food items of the Cheetah | 2
|  | Additional Cheetah's food information | This page contains at least five links to external resources with more details on individual food items. | 5
|  | Cheetah's gestation | Given I’m in a role of logged-in or guest user, When I open the "Mating&reproduction" page, the webpage containing the hyperlink to describe Cheetahs' gestional period must be displayed | 5
| Sprint 3 | Cheetah's offspring information | Given I’m in a role of logged-in or guest user, When I open the "Mating&reproduction" page, after the text of gestional period of the Cheetah, then the webpage show me the texts and pictures that describe the numbers of the cheetah’s offspring at a time. | 5
|  | Lifespan of Cheetah's offspring | Given I’m in a role of logged-in or guest user, When I open the "Mating&reproduction" page, in the last part, the webpage shows me the texts and that describes how long do the offspring live with the parent. | 5
|  | Cheetah's location | This page should contain the text and a map about the location and distribution of the Cheetah’s habitat. | 5
| Sprint 4 | Cheetah's survival and natural habitat information | This page should contain the text and at least 1 picture about the necessary and required natural surrounding for the Cheetah to thrive | 5
|  | Cheetah's habitat images | This page should contain the text and at least 1 picture about construction of Cheetah's home. | 5
|  | Cheetah's species images | There will be images of species of cheetah | 2
|  | Cheetah's classification | There will be information on the species and subspecies of Cheetah | 3
| Sprint 5 | Cheetah's scientific name and traits | There will be scientific name and characteristics of cheetah on the page in table format | 3
|  | Cheetah's size | There will be general size information below the image of cheetah | 2
|  | Cheetah's physical attributes | There will be unique physical characteristics of cheetah on the webpage | 2
|  | Cheetah's medical information | Lifespan and heart rate of the cheetah is mentioned in health part | 2
|  | Cheetah's hunting techniques | Hunting techniques of the cheetah is picturized | 1
|  | Blog on cheetah | Blog for cheetah's self protection is written with 3 pictures | 3
|  | Sleeping habits of Cheetah | Sleeping habits are shown in the form of text and images | 2
| Sprint 6 | Running the webpage | Each webpage must be tested to verify the data present. | 5
|  | Testing domain names | Each link must contain an existing domain name | 2
|  | Compling the code | Each line of the code must be tested to ensure accuracy | 2
|  | Content modification | The news in the home page must be updated every day. | 5
| Sprint 7 | Image manipulation | The pictures in the home page must be updated every alternate day | 3
|  | User-alerts | The users must be notified of the updates on the email address and social media accounts | 3
|  | User-communication/feedback | The user must be able to comment, like or dislike any information on the page | 1
|  | Sharing capability | The user must be able to share the links on other websites and social media accounts | 1
|  | Subscriptions/Registrations | A user must be able to register themselves through their social network accounts and connect with other users. | 3
| Sprint 8 | Cheetah live streaming | A user must be able to track the movements of Cheetah. A registered user must be able to record and download short clips while streaming | 4
|  |  | A guest user should be able to view the footage for only 2 hours. A registered user must gain unlimited access to the live stream. | 2
|  |  | A registered user must be able to engage in live chats with Cheetah experts and other users | 1